## Oct 14 Shoot
THE FOLD — October 14 shoot in LA with Marey. Order every prop by Thursday Oct 8. Links go straight to the source.
Item | Due | Status | Link
Props ordered (everything ordered by Thursday) | Thu Oct 8 | Not started | Prop list tab below
Location selection | October | Not started | The Fold — Social Media (Drive)
Flight details | Fri Oct 9 | Booked ✓ (Sep 17) | Southwest · CLKBM7 — see the Flight details tab
12 video examples delivered — Lavalle Sisters | Mon Oct 12 | Not started | Courtney drafted (Drive)
6 video examples delivered — The Fold | Mon Oct 12 | Not started | The Fold — October (Drive)
Photoshoot in LA with Marey | Wed Oct 14 | Not started | The Fold — November Cover Photos (Drive)
12 posts delivered to Courtney (post-shoot hand-off) | Fri Oct 16 | Not started | Courtney drafted (Drive)

## Flight details
THE FOLD — Flights for the October 14 shoot in LA with Marey. Booked September 17 on Southwest, confirmation CLKBM7.
Leg | Date | Route | Passengers
Outbound | Wed Oct 14 | SJC → LAX (San Jose → Los Angeles) | Kiabeth Cook · Kiaredza Lavalle
Return | Wed Oct 14 | LAX → SJC (Los Angeles → San Jose) | Kiabeth Cook · Kiaredza Lavalle
Seats assigned at check-in (Basic fare) — check in Tuesday Oct 13, 24 hours ahead.
Links
Confirmation email (Outlook · Meetings folder)
Manage flight — Southwest
Check in — Southwest

## Prop list
Props to order — everything ordered by Thursday Oct 8.
Prop | Qty | Order link | Ordered?
No
No
No
No
No
No
No
No
No
No

## Scripts — The Fold
THE FOLD. Courtney edits the Monday + Wednesday posts (6 a month); Kiabeth the rest. Board runs the dated Schedule.
Sarah's research question (verbatim) | Status | Post | Date | Platform | Brand | Script title | On screen (3-5 words) | Open (spoken hook) | Nugget 1 | Nugget 2 | Close (save / comment) | Caption + hashtags | Needs a fact from you